MVP plan and schedule

Scope:
v0 proves end-to-end viability on Astro-Databank C sample: ingest → entity resolve → fetch/clean bios → trait scoring → embeddings → astro features → basic statistics → downloadable report. Wellness UI is out of scope for v0.

Week 1 — Foundations & ingest

Mon 27 Oct → Sun 2 Nov 2025

Goals

- Bring up core infra and CI.

- Parse Astro-Databank XML to normalized rows.

- Define schemas and data contracts.

Deliverables

- Compose stack up: API, Worker, Postgres(+pgvector), Redis, MinIO, Grafana.

- Pydantic schemas for Person, Birth, Provenance.

- adb-xml-parse CLI: XML → person_raw + birth tables + raw XML to MinIO.

- Alembic migrations applied and versioned.

- Basic health endpoints: /healthz, /version.

Exit criteria

- You can upload the C sample and see rows in Postgres; raw XML in MinIO.

Week 2 — Enrichment & NLP

Mon 3 Nov → Sun 9 Nov 2025

Goals

- Entity resolution to Wikidata; fetch Wikipedia text; clean and store with licensing.

- Trait scoring rubric finalized; embeddings added.

Deliverables

- resolve-qid service: Name + DOB/Place → QID (with candidate JSON and score).

- fetch-bio service: QID → Wikipedia text + metadata (rev_id, lang, license).

- clean-bio pipeline: HTML/Wikitext → narrative paragraphs; language tag.

- score-traits worker: rubric → Big Five(+facets) JSON; strict schema & retry on parse.

- embed-bio worker: embeddings → pgvector column.

- Provenance table with attribution block generator.

Exit criteria

- ≥80% of sample gets QIDs automatically; cleaned bio text stored with attribution.

- Trait JSON and embeddings present for those records.

Week 3 — Astro features & statistics

Mon 10 Nov → Sun 16 Nov 2025

Goals

- Deterministic chart features; stats layer; negative controls.

Deliverables

- astro-features worker: positions, houses, standard aspects → flat feature vector.

- Stats job: correlations, BH-FDR, bootstrap CIs, permutation tests.

- Negative controls: shuffled DOBs and timezone jitter runs.

- Minimal dashboard: counts, completion, and top correlations table.

Exit criteria

- End-to-end job produces CSVs/Parquet + an HTML/PDF report with methods, tables, CIs.

Week 4 — Quality, reporting, and UX polish

Mon 17 Nov → Sun 23 Nov 2025

Goals

- Benchmarks vs a 30–50-person gold set; reproducibility; packaging.

Deliverables

- Gold set: human trait ratings; LLM vs human agreement (r, MAE, calibration plot).

- Version pinning: model name, prompt hash, data snapshot IDs.

- One-page file-upload UI (drag-and-drop), batch status page, report download.

- README with runbook, env, and “how to reproduce” script.

Exit criteria

- One command seeds sample → runs pipeline → produces report with negative controls.

- Agreement on gold set ≥0.6 for headline traits, or issues documented.